# The LJMU Framework for High Quality Teaching and Learning

## Overview and context

The LJMU Framework for High Quality Teaching and Learning is one of five strategic priorities from the university. It is underpinned by six requirements that will shape the focus of university activity, and is intended to be supportive, developmental, and to encourage self-reflection and continuous improvement.

The six requirements establish clear standards for driving forward teaching excellence, recognising and rewarding high-quality teaching, and importantly, addressing areas where improvement is required.

All staff who teach are expected to actively engage with the framework; and it is founded on the principle that all teachers have the capacity to continuously enhance their teaching and uphold the highest standards in delivering an outstanding student experience.

High quality teaching and learning involves educational practices that effectively support all students to achieve deep understanding, critical thinking, skill development, and personal growth. It's not just about delivering content, it's about how learning happens, the relationships in the classroom, and beyond, and importantly strong outcomes for students.

High quality teaching and learning in the context of LJMU should be centred around engaging students as active participants in their education and be supported by research-informed, inclusive, and reflective teaching. Raising the quality of teaching requires both individual staff commitment alongside systemic institutional support to foster a culture of continuous improvement

One of the institutional key performance indicators in Strategy (2030) is for LJMU to be 2.5% above the sector benchmark for teaching on my course. Whilst this metric is defined in the context of the National Student Survey (NSS), it is also an expectation of the Postgraduate Taught Experience Survey (PTES), and Postgraduate Research Experience Survey (PRES) too.

Whilst the university are on a year on year upward trajectory on the teaching on my course metric, the sector is rising at a faster pace. Consequently, this impacts the profile of LJMU in quality assurance, enhancement, and reputational terms. Moreover, providing students with the very best teaching is critical to an outstanding student experience and the pace of change must increase.

The time is now right to double down on our commitment to delivering high quality teaching and learning that provides all learners with intellectual challenge and strong outcomes. The Framework for High Quality Teaching and Learning sets out the expectations of our staff in delivering on a key strand in the Education and Student Experience Plan (ESEP) (2023 – 2030).

## The LJMU Framework for High Quality Teaching and Learning

The framework requirements are intended to shape the tone and culture of our institution moving forward. In doing so, the six requirements are intended to establish clear standards for driving forward teaching excellence, recognising and reward high-quality teaching, and importantly addressing areas where improvement is required.

Defining high quality teaching and learning

Setting expectations

Framework for high quality teaching learning

Qualified to teach

Quality assurance and enhancement

Intellectual challenge

Reward and recognition

All staff who teach are expected to actively engage with the framework. It is founded on the principle all teachers have the capacity to continuously enhance their teaching and uphold the highest standards in delivering an outstanding student experience.  Whilst the framework is intended to be supportive, developmental, and encourage self-reflection and continuous improvement, it equally is important to tackle poor performance.

The university continues to build on its commitment to high quality teaching, and student outcomes. However, if we are to deliver on our TEF Gold ambitions, we must increase the pace and focus of our enhancement activity. This will require a collective effort and commitment from our staff, University, and Executive Leadership Team Student Union (JMSU), and our students.

## Advancing Teaching Excellence and Student Success

The university is committed to reinforcing its TEF Gold aspirations by positioning itself within the ‘TEF Triple Gold Patterns of Excellence’  evidence-based publication. This requires not only evidencing change, enhancement, and impact, whilst equally foster more proactive engagement with student survey tools such as the NSS, PTES, and PRES.

By explicitly articulating to students what intellectually stimulating and high-quality teaching is, this will strengthen recognition and confidence in the university teaching provision. Central to this ambition is the student voice and partnership agenda.

By working collaboratively with JMSU, the university will review student feedback mechanisms to ensure they are effective, transparent, and responsive. This will strengthen engagement and create a genuine sense of partnership between students and staff, ensuring feedback is acted upon and visibly shapes teaching enhancement.

The Framework for High Quality Teaching and Learning will be overseen by a Teaching Quality Board chaired by the Pro-Vice Chancellor (Student Experience). This will provide leadership, oversight, assurance, and accountability for high standards of teaching across the university.

# The LJMU Framework for High Quality Teaching and Learning

| Requirement | What this means for LJMU | Intention | Action | Responsibility and evidence | Timeline |
| --- | --- | --- | --- | --- | --- |
| Define ‘high quality teaching and learning’ at LJMU. | High quality teaching and learning (HQTL) is evidenced through intentional, inclusive, and intellectually challenging educational practices that promote deep understanding, critical inquiry, and independent thought. HQTL prepares students not just to absorb knowledge, but to contribute to it, and is characterised by: - Clear and coherent curriculum design. - Students understanding what is expected of them to gain successful outcomes. - Engaging research informed teaching. - Inclusive and student-centred learning - Development of critical thinking and independence. - Constructive feedback and assessment. - Supportive learning environments. | - Definition (and Framework for HQTL) to be published in all relevant policies, practices. | - Discuss the Framework with Academic Registry with the expectation this is integrated into all future validation and review events and documentation | - PVC SE and RCOO. - Evidenced through validation and review guidance and/or documentation, chairs briefings, and reports, and publication of the annual institutional validation and review paper. | Oct. 2025 |
|  |  |  | - Integrate the Framework for HQTL into ESEP and TLA Plan to form one document. | - PVC SE and Dean of TLA. - Evidenced through policies, ESEP, and on TLA website. | Oct. 2025 |
|  |  | - School Directors to ensure all academic staff can articulate the definition within their teaching and learning. | - Framework communicated to school and faculty leaders at a face-to-face directorate and followed up with a written briefing note. | - PVCSE, School Directors, ADESE, and Faculty PVCs. - Directorate meeting takes place and minutes record discussion - Teaching Quality Board to receive a quarterly report on school activity from ADESE | ULT 10/25 CME 07/26 Teaching Board -12/25, 04/26, 07/26, 09/26 |
|  |  |  | - Framework implementation reported through CME and quarterly Teaching Quality Board meetings. | - Directors and ADESE - Directors and ADESE to report on implementation through CME. - Teaching Quality Board to receive quarterly reports on school activity. | Jul. 2026 for CME Teaching Board -12/25, 04/26, 07/26, 09/26 |
|  |  |  | - Six-point model introduced for programmes and schools to raise student survey outcomes to be communicated to all school directors. | - PVCSE - Communication of survey approach as part of Directorate meetings. - Follow up discussions in FESEC’s and through Faculty PVC and School Director meetings during academic year. | Oct. 2025 |
|  |  | - HQTL definition to be used as an assessment measure during mandatory observation of teaching. | - HQTL Framework (and definition) to be reported upon and assessed in teaching observations. | - Dean TLA and PVC SE to review observations progress at Teaching Quality Board meetings - School Directors and HRBP to be responsible for acting on the outcomes of observations. - Note: Mandatory observations could initially focus on where there is need for immediate action. This could act as a pilot for a wider observation scheme and help understand how the process would work and implications for managing this at scale. - Note: Costs could be embedded in existing workload allocations if prioritised and costs would then be minimal. | Teaching Board -12/25, 04/26, 07/26, 09/26 Directors and HRBP meetings ongoing |
|  |  |  | - Teaching observer training and written guidance will include discussion of HQTL definition and how it can be measured. | - Dean TLA, NTF Network, Faculty PVC - Training guidance published. - Criteria established to support schools in prioritising teaching observations (based on survey metrics and longitudinal data). | Oct 2025 for training guidance and priority observations |
|  |  | - School CME to comment on how the definition is being delivered and evaluated annually. | - Academic Registry to revise the CME documentation to add a requirement to comment in programme and school reports on how HQTL is being addressed. | - Directors and ADESE to report on implementation through CME. - CME outcomes to be discussed at Teaching Quality Board meetings | July 2026 for CME Teaching Board -12/25, 04/26, 07/26, 09/26 |
|  |  | - TLA to run development programmes on HQTL. | - Teaching Insight Seminar Series to run monthly with a focus for the academic year on HQTL. | - NTF Network and Dean TLA - Teaching insight seminars to be advertised and promoted through schools and ADESEs | Sept 2025 to July 2026 |
|  |  |  | - PG Cert lectures on HQTL to be promoted to all academic staff. | - PG Cert to be promoted to schools via Dean TLA | Sept 2025 to July 2026 |
|  |  |  | - Publication of online web resources on what is HQTL | - Dean TLA to establish online resources | Nov 2025 |
|  |  | - Teaching on my course measures to increase year on year above sector positivity score. | - Subject level NSS teaching scores to rise above sector average annually | - School Directors and Programme Leaders - TLA to continue to produce institutional oversight reports - Teaching Quality Board and ESEC to report on outcomes of surveys and report findings and actions to ELT | July 2026 |
|  |  |  | - Institutional NSS teaching scores to rise above sector average annually |  |  |
|  |  |  | - PTES teaching quality scores to rise in line with the sector. PRES supervision, research skills and development to rise above sector average. |  |  |
| Set out expectations of how to raise the quality of teaching and learning. | Improvement requires individual academic staff to: - Participate in teaching enhancement programmes (including direct observation) - Engage actively with learning analytics to enhance HQTL. - Apply student engagement data and course evaluations to enhance HQTL. - Design teaching for active learning. - Incorporate case studies, discussions, simulations, and/or group work to move beyond passive lectures. - Be reflexive and student aware. - Consistently reflect on what works, listen to feedback, and adapt methods. Improvement requires Directorate, and executive level to: - Support a culture of teaching excellence and evidence-based practice. - Value teaching excellence equally to research. - Reward innovative pedagogy and mentorship. - Foster collaboration and sharing of best practice. - Facilitate access to technology, inclusive learning spaces, and learning support. - Embed Quality Assurance and Enhancement into HQTL. - Embed HQTL discussions within the appraisal process - Use regular course review, student feedback loops, and external benchmarking to refine curriculum and delivery. | - Setting expectations will require a collaborative effort and commitment between individual academics, schools, professional services, directorate and ELT. | - School directors to provide leadership focus on setting expectations of academic staff in school and programme meetings. | - School Directors, Dean TLA - Evidence of discussion in meeting minutes. - Teaching staff can articulate strategies to raise teaching quality | October 2025 |
|  |  |  | - Academic appraisals to address individual staff expectations and record these in Actus. | - School Directors and HR - Staff Actus files to be reviewed by HRBP to identify evidence of discussion in appraisals. | Aug. 2026 |
|  |  | - Two ‘School Teaching Enhancement Review Meetings’ led by National Teaching Fellows will take place each academic year. | - Arrange School Teaching Enhancement Reviews. | - Dean TLA, NTF Network - Notes of reviews captured along with report outcomes and sharing of best practice. | October 2025 |
|  |  |  | - NTF Network to collate an annual best practice report on teaching excellence. | - NTF Network - Best practice report produced and discussed at relevant governance meetings. | July 2026 |
|  |  | - Evidence based strategies and outcomes to report through CME (including engaging in research informed teaching development and review). | - Academic Registry to review programme and school CME guidance to ensure narrative is evidence based. | - RCOO and PVC SE - Report produced by Academic Registry and Dean TLA on quality assurance and Quality enhancement of CME. | July 2026 |
|  |  |  | - Academic Registry to ensure research informed teaching and observation of teaching are commented on in CME. | - RCOO and PVC SE - Report produced by Academic Registry and Dean TLA on quality assurance and Quality enhancement of CME | July 2026 |
|  |  | - PVC Student Experience to organise three Director of School meetings each academic year with a focus on HQTL. Purpose will be to share best practice, challenges, blockers, and opportunities | - Schools to work on rotation to present information on best practice, challenges, blockers, and opportunities at meetings. | - PVC SE - Notes of meetings and outcomes reported to ESEC and ELT | Meetings 10/25, 01/26, 05/26 |
|  |  |  | - Teaching Quality Board to report to ESEC on a quarterly basis on issues and actions arising from Directorate meetings. | - PVC SE - Teaching Quality report evidence topics discussed, lessons learned, and actions to take forward. | 12/25 04/26 07/26 09/26 |
|  |  | - Directors of School to work with the HRBP to identify outstanding teachers, and those who need guidance and support. | - Directors to meet with HRBP to discuss teaching quality performance concerns and agree actions. | - Exec Dir HR and Directors of School - HRBP and Directors can evidence HQTL performance discussions and actions have taken place. | Oct. 2026 and ongoing |
|  |  |  | - HR to hold a record of school and institutional teaching performance reviews requiring formal intervention. | - Exec Dir HR and Directors of School - Report shared with Exec Dir HR and communicated to ELT as required. | Mar. 26 |
|  |  |  | - Directors to work with PVC SE and HRBP to identify high performing teachers and review career trajectory. | - Exec Dir HR, Directors of School, and PVC SE - List of high performing teachers identified, and appropriate mentoring and recognition put in place. | Feb. 2026 |
|  |  | - Re-establish an annual teaching and learning awards ceremony to recognise best practice. | - SATH Conference to introduce a recognition event to celebrate and share best practice | - Dean TLA - News stories and list of colleagues and teams celebrated | Jun. 2026 |
|  |  |  | - Annual Staff Celebration Event to enhance the focus on celebrating teaching quality. | - Exec Dir HR and PVC SE - Event has a higher profile on HQTL and recognition of teachers who have excelled. | Jun. 2026 |
| Ensure all staff are qualified to teach and define what is expected at LJMU. | The OfS Condition B2 (Resources, support and student engagement) requires staff to be ‘appropriately qualified’. At LJMU we require staff who teach to have: - Expert knowledge of the subject they design and deliver. - Be qualified to teach via academic qualifications and professional development. - Teaching experience, appropriate for the content and level of the course. - Required knowledge and skills for the effective delivery of outstanding teaching. - A minimum of Fellowship of HEA with a plan to enhance this further. | - Establish school targets for Fellowship and beyond of the Higher Education Academy. | - TLA and NTF Network to propose school targets in discussion with Directors of School. | - Dean TLA - Notes of meetings to evidence discussion and school targets to be reported to ESEC. | Nov. 2025 |
|  |  |  | - Fellowship targets and outcomes to be reported on a 6 monthly basis to ESEC | - Dean TLA - Report produced and discussed at ESEC with minutes and papers as evidence. | Apr. and Oct. 2026 |
|  |  | - Establish school targets for staff qualified to teach (i.e., PG Cert TLHE, MA, 3i’s). | - TLA, HR, and NTF Network to review school targets in discussion with Directors of School. | - Exec Dir HR, Directors of School, and PVC SE - Notes of meetings to evidence discussion and school targets to be reported to ESEC. | Nov. 2026 |
|  |  |  | - Staff qualifications to be reported annually by HR and PVC SE. | - Exec Dir HR and PVC SE - Annual report produced and presented to ESEC, ELT, and Employment Committee | Jun. 2026 |
|  |  | - Staff qualifications and fellowships to be detailed in the annual school CME process including strategies for raising these further. | - Academic Registry to add a section into CME to record staff fellowships. | - RCOO - CME will be able to evidence staff fellowships and school plan to enhance these further. | Nov. 2025 |
|  |  | - Job descriptions to be revised to reflect the above. | - PVC SE and HR to ensure job descriptions are reviewed to clearly state this expectation as part of recruitment and probation. | - PVC SE and Exec Dir HR. - Revised job descriptions produced, and recruitment and probation process reviewed to strengthen teaching qualification expectation. | Nov. 2026 |
|  |  |  | - HR to review staff teaching qualifications by school and discuss with Directors of School | - Exec Dir HR - Meeting and action notes will evidence discussion and forward plans. | Jun. 2026 |
|  |  |  | - Annual report on teaching qualifications to be presented to Employment Committee and ESEC. | - Dean TLA and PVC SE - Report presented at relevant meetings along with an action plan for further enhancement. | Jun. 2026 |
| Establish a Reward and Recognition Framework for Outstanding Teaching and Learning. | Setting clear expectations of staff and providing support to help them achieve by: - Appointing staff qualified to the level above which they teach. - Monitoring of staff development attendance and research informed teaching through the appraisal process. - Within two years of starting at LJMU all contracted academic staff must obtain an appropriate teaching qualification and/or apply for accreditation by Advance HE. | - Directorate to use the HEA ‘Embedding reward, recognition and promotion in teaching & learning’ - publication to guide staff development. | - TLA and HR to work with School Directors to discuss the HEA document and its application to staff development in the school. | - Exec Dir HR, Directors of School, Dean TLA - Directors to evidence dissemination of HEA document to school staff. - At least one development seminar per school each academic year. | Oct. 2025 Ongoing |
|  |  |  | - Directors to ensure professional development needs in teaching and learning are discussed within appraisals. | - Director of School and HRBP - Actus staff records should evidence discussion with line mangers. - HRBP to discuss with managers the impact and outcomes of discussions. | Jun. 2026 Ongoing |
|  |  | - National Teaching Fellows to be recognised as Readers in Teaching and Learning and given a fast-track mentor to coach them to Professorship. | - NTF’s to be briefed as appropriate to current role on the process for recognition. | - PVC SE - 11 NTFs briefed on strategic intent to enhance HQTL. | Oct. 2025 |
|  |  |  | - Creation of process to recognise NTFs as Readers | - PVC SE and PVC RKE - 11 NTFs roles reviewed and discussion with Faculty PVC to set up fast track to Readership | Oct. 2025 |
|  |  |  | - PVC SE and PVC RKE to create a mentoring process with NTFs on a fast-track process to Professorship. | - PVC SE and PVC RKE - NTF roles reviewed and in discussion with Faculty PVC plans are put in place to fast track to Professorship | Nov. 2025 |
|  |  | - Academic promotion route to be appropriately resourced | - ELT led by the FD to discuss resourcing mechanisms to recognise and reward staff under the academic promotion route. | - FD and Faculty PVC - Assessment of whether funds are in place to support academic promotion in a manner that matches the conferment process for Readership and Professorship. | Oct. 2025 |
|  |  | - Schools to identify early career Reader and Professorship pipeline in Teaching and Learning. | - Criteria to be established to identify future Reader and Professors. | - PVC SE, PVC RKE, Faculty PVC, HR - Criteria established and communicated to staff. | Dec. 2025 |
|  |  |  | - Mentoring programme established | - PVC SE, Exec Dir HR - Mentoring programme established and evidence of staff attending and outcomes being achieved. | Dec. 2025 |
| Monitor and report on teaching quality assurance and enhancement | Governance structures (Academic Board, ELT, ESEC, FESEC, CME) to receive reports that analyse, and act upon reviews of delivery of HQTL. These reports will be critical for evidence-based interventions supporting strong outcomes. Reports will be used to enhance communications on teaching and learning such as: - Creating and distributing engaging content across digital channels. - Showcase achievements and impact by highlighting research, teaching, student success stories, and staff accomplishments. - Amplify institutional reputation to boost visibility, support recruitment, and attract funding through compelling narratives that demonstrate outcomes. - Enhanced visibility and scrutiny of HQTL in quality processes such as CME, external examiner reports, and module review. | - Mandatory teaching observations for all staff who teach. | - Teaching Quality Board established to monitor and review the outcomes of teaching observations. | - PVC SE - Teaching Quality Board meets on a quarterly basis with a standing item on teaching observation. - External adviser/s to be recruited to attend Board meetings | Board meetings scheduled 12/25 04/26 07/26 09/26 |
|  |  |  | - Directors to ensure all staff who teach are formally observed at least once annually. | - Directors and managers - Teaching staff list to be regularly reviewed and discussed between HRBP and Director and managers - Evidence of interventions to address poor performance and excellent teaching. | Oct. 2025 and ongoing |
|  |  | - Directors to identify circa 20% of academic staff to undertake HQTL teaching observations against set criteria. | - Directors to work with HRBP and TLA to identify teaching observers against set criteria. | - Directors and Dean TLA - Observer qualifying criteria developed and shared with Directors | Oct. 2025 and ongoing |
|  |  |  | - Directors to ensure observers receive appropriate time to undertake observations. | - Directors - Observers to receive sufficient time to undertake observations and feedback. - Teaching observation recognised as part of reward and recognition. | Oct. 2025 and ongoing |
|  |  | - ESEC to receive an annual report on teaching observations. | - ADESE to work with Directors to produce a report to be presented to Teaching Quality Board and ESEC. | - ADESE and School Directors - Structure of faculty reports to be determined as a minimum expectation. - Actions from annual report addressed and positive outcomes evidenced. | Jan. 2026 |
|  |  | - School CME to report on teaching observations. | - Academic Registry to revise CME for School level reports to comment on direct observation of teaching as well as peer observation. | - RCOO - HQTL (i.e. qualified to teach, evidence-based analysis, professional development) built into Actus for teaching staff. - CME process updated to report on teaching observations. | Feb. 2026 |
|  |  | - CCSR to work with PVC Student Experience and Directors to raise the profile of HQTL and increase positive messaging on excellence. | - CCSR to develop a communication plan of key events and activity to promote high quality teaching and learning. | - PVC EEP and PVC SE - Communication plan discussed at Teaching Quality Board meetings. - Communication plan shared across the university community (student and staff). | Nov. 2025 |
|  |  |  | - Visibility and messaging on high quality teaching and intellectual stimulation to be enhanced across the campus. | - PVC EEP, PVC SE, and NTF Network - Positive news stories and visibility enhanced across the university campus. - Communications have a focus on what outstanding teachers are and do. Messaging to focus on HQTL including intellectual stimulation. | Nov. 2025 |
|  |  |  | - CCSR to work with Directors of School to create materials that are subject focused and are targeted at students. | - PVC EEP and School Directors - School and subject focused materials developed. - Explore student internships to work with CCSR and subject areas to develop relevant resources | Nov. 2025 |
| Enhancing intellectual stimulation, challenge and criticality | Teaching must be intellectually stimulating and challenging, and academic staff must be able to evidence this through: - Encouraging students to question, debate, and explore complexity. - Exposing students to current real-world problems and varying perspectives. - Providing opportunities for critical thinking beyond content consumption. - Demonstrating how your discipline is dynamic, evolving, and relevant. - Designing sessions and tasks using open questions to push learners to evaluate, challenge assumptions, and build arguments (incl. RIT accelerator events) | - Teaching and Learning Academy to deliver CPD on intellectual stimulation. | - Teaching Insights Seminars to have a focus on intellectual stimulation and HQTL. | - Dean TLA - Teaching Insights Seminars evidence intellectual stimulation sessions as part of programmed events. | Oct. 2025 onwards |
|  |  |  | - TLA to develop online resources on intellectual stimulation. | - Dean TLA and NTF Network - Online resources developed and published on TLA webpages - ADESE to identify best practice for dissemination. | Oct. 2025 onwards |
|  |  | - Directors to ensure staff who teach have a clear focus and expectation on quality teaching as well as intellectually stimulating student discussion. | - School Directors to ensure Programmes address intellectual stimulation within teaching and learning. | - Director of School - Intellectual stimulation discussed as part of curriculum review and staff development days. | Oct. 2025 onwards |
|  |  | - Intellectual stimulation to be a core aspect of teaching observations. | - Intellectual stimulation to be a core strand of teaching and peer observations. | - Dean TLA - Observation process has a strand on intellectual stimulation that is assessed and discussed during feedback process. | Oct. 2025 onwards |
|  |  | - Staff who teach to ensure intellectual stimulation and challenge is discussed with students. | - Programme Leaders to ensure intellectual stimulation is discussed with students. | - Director of School and Programme Leaders - Module appraisals evidence student commentary on intellectual stimulation and challenge. - Positive free text comments and an evident upward trajectory in NSS outcomes. | Nov. 2025 onwards |

Darling-Hammond, L., 2021. Defining teaching quality around the world. European Journal of Teacher Education, 44(3), pp.295-308.

Harrison, R., Meyer, L., Rawstorne, P., Razee, H., Chitkara, U., Mears, S. and Balasooriya, C., 2022. Evaluating and enhancing quality in higher education teaching practice: A meta-review. Studies in Higher Education, 47(1), pp.80-96.

LJMU Teaching and Learning Plan (2023 – 2030), https://www.ljmu.ac.uk/-/media/staff-intranet/academic-registry/files/policy-page/lta23--for-website.pdf

LJMU Strategy 2023 – 2030, https://www.ljmu.ac.uk/about-us/our-vision-and-values/mission-and-strategy

Four questions contribute to ‘Teaching on my Course’ – 1. How good are teaching staff at explaining things?

2. How often do teaching staff make the subject engaging?  3. How often is the course intellectually stimulating?

4. How often does your course challenge you to achieve your best work?

Quality of supervision and training

Advance HE, 2024, Teaching Excellence Framework:  2023: Patterns of Excellence, https://www.advance-he.ac.uk/news-and-views/tef-2023-patterns-excellence-reveals-features-common-gold-achievers